## Sprint8(Banking Mortgage Loan)
Q3-Appian Sprint8 WBS(01-08-2023 to 12-08-2023)
Updated version for Banking Mortgage Loan Processing , Use Case - Automobile Procurement Processing
Module | Operation | Interfaces & Process Models Required | Complexity | Assigned To | Planned- Start Date | Planned-End Date | Actual Start Date | Actual End Date | Effort In Hours(Planned) | Actual Hours
| Gathering Requirements from Bank Consultant |  | Medium | Bala/Akhila | 2023-08-01 | 2023-08-01 |  |  | 16
Validations
| Age requirement | Yes | Medium | Akhila | 2023-08-02 | 2023-08-03 |  |  | 12
| Annual Income based Conditions | Yes | Medium | Akhila | 2023-08-03 | 2023-08-04 |  |  | 8
| Property value Based Conditions | Yes | Medium | Akhila | 2023-08-04 | 2023-08-05 |  |  | 12
Loan Application
| create File Uploading Fields | Yes | Medium | Bala | 2023-08-02 | 2023-08-02 |  |  | 8
Loan Approval
| Processing level | Yes | Medium | Bala | 2023-08-03 | 2023-08-04 |  |  | 12
| Manager level | Yes | Medium | Bala | 2023-08-04 | 2023-08-05 |  |  | 12
Use Case - Automobile Procurement Processing
Product | Identify a need for products and/or services | Yes | Medium | Akhila | 2023-08-07 | 2023-08-07 |  |  | 8
| Creating products | Yes | Medium | Akhila | 2023-08-08 | 2023-08-09 |  |  | 10
| Updating products | Yes | Medium | Akhila | 2023-08-09 | 2023-08-10 |  |  | 8
| Getall Products | Yes | Medium | Akhila | 2023-08-10 | 2023-08-11 |  |  | 10
UI | Creating Request Form | Yes | Medium | Bala | 2023-08-07 | 2023-08-07 |  |  | 8
| Creating Order form | Yes | Medium | Bala | 2023-08-08 | 2023-08-08 |  |  | 8
Supplier | Evaluate and select suppliers/vendors. | Yes | Medium | Bala | 2023-08-09 | 2023-08-09 |  |  | 6
| Creating Supplier | Yes | Medium | Bala | 2023-08-09 | 2023-08-10 |  |  | 6
| GetAll Supplier | Yes | Medium | Bala | 2023-08-11 | 2023-08-12 |  |  | 8
| DEMO ON USECASE |  |  |  | 2023-08-12 |  |  |  | 8

## Sprint 9
Q3-Appian Sprint9 WBS(14-08-2023 to 26-08-2023)
The updated version for Automobile Procurement Processing , Self-Learning
Module | Operation | Interfaces & Process Models Required | Complexity | Assigned To | Planned- Start Date | Planned-End Date | Actual Start Date | Actual End Date | Effort In Hours(Planned) | Actual Hours
Purchase | Negotiate the terms of a contract with the selected supplier. | Yes | Hard | Akhila | 2023-08-14 | 2023-08-15
| Access and select vendors | Yes | Hard | Akhila | 2023-08-15 | 2023-08-17
Order | Finalize a purchase order. | Yes | Medium | Bala | 2023-08-16 | 2023-08-17
| Appian-API,Process Model,Interfaces Integration |  | Medium | Akhila/Bala | 2023-08-18 | 2023-08-18
| DEMO ON USECASE |  |  |  | 2023-08-19
|  | Self-Learning |  | Akhila/Bala | 2023-08-21 | 2023-08-26