## Appian Sprint 1 Estimation
Appian- Work Breakdown Structure
|  |  | Planned Date |  | Actual Date
Sr. No | Features | Assign To | Start Date | End Date | Start Date | End Date | Efforts in Hours | Actual hours | Status | % Complete | Comment
Sprint 1 - (03-04-2023 to 14-04-2023)
| Appian Courses | [5 empty] | TOTAL HRS
Introduction to Appian
| Appian Essentials |  | 2023-04-03 | 2023-04-04 | 2023-04-03 | 2023-04-04 | 2 | 2 | Completed | 100%
| Introduction to delivery methodology | Akhila&Bala&Madhan&Suba | 2023-04-03 | 2023-04-04 | 2023-04-03 | 2023-04-04 | 5 | 4 | Completed | 100%
| Database design Basics |  | 2023-04-03 | 2023-04-04 | 2023-04-03 | 2023-04-04 | 4 | 5 | Completed | 100%
| Application Architecture-Design a sample App |  | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-05 | 4 | 5 | Completed | 100%
| Create an application-Steps |  | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-05 | 5 | 4 | Completed | 100%
| Module Feedback/Evaluation -Clarification and Analysing Understanding of concepts |  | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-05 | 4 | 4 | Completed | 100%
Application Building Blocks
| Manage Users and Groups |  | 2023-04-06 | 2023-04-07 | 2023-04-06 | 2023-04-07 | 2 | 3 | Completed | 100%
| Expressions-Transform Your Data |  | 2023-04-06 | 2023-04-07 | 2023-04-06 | 2023-04-07 | 3 | 2 | Completed | 100%
| Design Application Records part 1 | Madhan & Bala | 2023-04-06 | 2023-04-07 | 2023-04-06 | 2023-04-07 | 4 | 4 | Completed | 100%
| Design Application Records part 2 |  | 2023-04-07 | 2023-04-10 | 2023-04-06 | 2023-04-07 | 3 | 2 | Completed | 100%
| Create user experience with sites and portals |  | 2023-04-07 | 2023-04-10 | 2023-04-07 | 2023-04-10 | 3 | 4 | Completed | 100%
| Query your data |  | 2023-04-07 | 2023-04-10 | 2023-04-07 | 2023-04-10 | 3 | 3 | Completed | 100%
| Build Forms And Other Interface |  | 2023-04-07 | 2023-04-10 | 2023-04-07 | 2023-04-11 | 3 | 3 | Completed | 100%
| Module Feedback/Evaluation -Clarification and Analysing Understanding of concepts |  | 2023-04-10 | 2023-04-12 | 2023-04-11 | 2023-04-12 | 3 | 3 | Completed | 100%
| Knowledge Transfer & Learning+Practicing Concepts |  | 2023-04-11 | 2023-04-12 | 2023-04-10 | 2023-04-12 | 8+8 | 7+9 | Completed | 100%
Workflow And Reports
| Process Modelling-Automate your process | Akhila & Suba | 2023-04-06 | 2023-04-07 | 2023-04-06 | 2023-04-07 | 6 | 7 | Completed | 100%
| Build Basic Charts And Grids |  | 2023-04-06 | 2023-04-07 | 2023-04-06 | 2023-04-07 | 6 | 5 | Completed | 100%
| Module Feedback/Evaluation -Clarification and Analysing Understanding of concepts |  | 2023-04-06 | 2023-04-07 | 2023-04-06 | 2023-04-07 | 3 | 3 | Completed | 100%
| Knowledge Transfer & Learning+Practicing Concepts |  | 2023-04-11 | 2023-04-12 | 2023-04-11 | 2023-04-12 | 8 | 8 | Completed | 100%
Intermediate Interface Design
| Building Dynamic Interfaces | Akhila & Suba | 2023-04-07 | 2023-04-10 | 2023-04-07 | 2023-04-11 | 6 | 5 | Completed | 100%
| Module Feedback/Evaluation -Clarification and Analysing Understanding of concepts |  | 2023-04-07 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 3 | 4 | Completed | 100%
| Knowledge Transfer & Learning+Practicing Concepts |  | 2023-04-11 | 2023-04-12 | 2023-04-11 | 2023-04-12 | 8 | 8 | Completed | 100%
Optional Courses-Interfaces
| Build Complex Interfaces by Adapting Patterns |  | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2 | 2 | Completed | 50% | Need to explore a lot-Still some concepts pending
| UX Design and Appian |  | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2 | 2 | Completed | 50% | Need to explore a lot-Still some concepts pending
| Write data with custom data types | Akhila&Bala&Madhan&Suba | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2 | 2 | Completed | 50% | Need to explore a lot-Still some concepts pending
| Project-Build an IT Application |  | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 1 | 1 | Completed | 50% | Need to explore a lot-Still some concepts pending
| Module Feedback/Evaluation -Clarification and Analysing Understanding of concepts |  | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 1 | 1 | Completed | 50% | Need to explore a lot-Still some concepts pending
Associate developer certification
| Associate Developer certification practice test | Akhila&Bala&Madhan&Suba | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 8 | 8 | Completed | 100%

## Appian Sprint 2 Estimation
Appian- Work Breakdown Structure
|  |  | Planned Date |  | Actual Date
Sr. No | Features | Assign To | Start Date | End Date | Start Date | End Date | Efforts in Hours | Actual hours | Status | % Complete | Comment
Sprint 2 - (18-04-2023 to 28-04-2023)
| Appian Courses | [5 empty] | TOTAL HRS
Appian Interfaces
| Interfaces Build Complex |  | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 4 | 3 | Completed | 100
| UX Design and Appian | Akhila&Bala&Madhan&Suba | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 4 | 5 | Completed | 100
| Write Data with custom data types |  | 2023-04-19 | 2023-04-19 | 2023-04-19 | 2023-04-19 | 5 | 5 | Completed | 100
| Appian Developer Project:Build an IT Application |  | 2023-04-19 | 2023-04-21 | 2023-04-19 | 2023-04-21 | 3+8+4=15 | 16 | Completed | 100
| Module Feedback/Evaluation -Clarification and Analysing Understanding of concepts |  | 2023-04-21 | 2023-04-21 | 2023-04-21 | 2023-04-21 | 4 | 3 | Completed | 100
Appian UseCase on Action Item Tracker
Description:Design a system to assign, update, and finish the action items that have been assigned to a person.
Roles Involved: Project Members, Project Lead
| 1.Development of UI Screens for Action Tracker |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 2 | Completed | 100
| 2.POST Method-Create Action |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 2 | Completed | 100
| 3.POST Method-Add Notes |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 3 | Completed | 100
| 4.POST Method-Add/Update Status |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 3 | Completed | 100
| 5.GetAll Method- Action Item Tracker |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 3 | Completed | 100
| 6.GetSummary By Action Id- Action Tracker | Akhila&Bala&Madhan&Suba | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 3 | Completed | 100
| 7.GetAll Method- Notes |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 | 8+8+8+8=32 | 3 | Completed | 100
| 8.GetDocument Details By Notes Id- Action Tracker-Document |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 2 | Completed | 100
| 9.GetAll Method- Action Item Tracker-Priority |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 3 | Completed | 100
| 10.GetAll Method- Action Item Tracker-Status |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 2 | Completed | 100
| 11.Development Of Entity class with Entity Relationship |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 2 | Completed | 100
| 12.Development Of Business Process- Action Item Tracker -Appian |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 2 | Completed | 100
| 13.End To End Testing |  | 2023-04-24 | 2023-04-27 | 2023-04-24 | 2023-04-27 |  | 2 | Completed | 100
| UseCase Feedback -Clarification and Analysing the Understanding on Usecase |  | 1hr on daily basis | [5 empty] | Completed | 100
| Demo On the UseCase |  | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 8 | 8 | Completed | 100
MILESTONE
To complete Interface courses and to complete usecase on Action Item Tracker

## Appian Sprint 3 Estimation
Appian Sprint 3 WBS(05-05-2023 to 18-05-2023)
Use Case-Order Fulfillment
Module | CRUD | Fields | Interfaces & Process Models Required | Complexity | Assigned To | Planned- Start Date | Planned-End Date | Actual Start Date | Actual End Date | Effort In Hours(Planned) | Actual Hours
Product:
| Create Product | ProductId |  |  |  | 2023-05-05 | 2023-05-05 |  |  | 4
| Update Product | ProductName |  |  |  | 2023-05-05 | 2023-05-05 |  |  | 4
| Getall Product | ProductType | Yes | Medium | Bala/Madhan | 2023-05-06 | 2023-05-06 |  |  | 4
| Delete Product | ProductPrice |  |  |  | 2023-05-06 | 2023-05-06 |  |  | 4
| GetProductByuser | UserId |  |  |  | 2023-05-08 | 2023-05-08 |  |  | 8
Order
| Create Order | OrderId |  |  |  | 2023-05-05 | 2023-05-05 |  |  | 4
| Update Order | OrderQuantity | Yes |  |  | 2023-05-05 | 2023-05-05 |  |  | 4
| Getall Order | DueDate |  | Medium | Akhila/Madhan | 2023-05-06 | 2023-05-06 |  |  | 4
| Delete Order | ItemName |  |  |  | 2023-05-06 | 2023-05-06 |  |  | 4
| GetOrderByCustomer | CustomerId |  |  |  | 2023-05-08 | 2023-05-08 |  |  | 8
| GetOrderByUser | UserId |  |  |  | 2023-05-09 | 2023-05-09 |  |  | 8
| GetOrderByProduct | ProductId |  |  |  | 2023-05-10 | 2023-05-10 |  |  | 8
[6 empty] | 2023-05-11 | 2023-05-11 |  |  | 4
Customer
| Create Customer | CustomerId |  |  |  | 2023-05-05 | 2023-05-05 |  |  | 8
| Update Customer | CustomerName |  | Medium |  | 2023-05-06 | 2023-05-06 |  |  | 8
| Getall Customer | CustomerPhoneNo | Yes |  |  | 2023-05-08 | 2023-05-08 |  |  | 8
| Delete Customer | CustomerMailId |  |  | Subha/Madhan | 2023-05-09 | 2023-05-09 |  |  | 8
| GetProductByCustomer | ProductId |  |  |  | 2023-05-10 | 2023-05-10 |  |  | 8
| GetOrderByProduct | OrderId |  |  |  | 2023-05-11 | 2023-05-11 |  |  | 8
Integration | Inteerfaces,Api,ProcessModel |  |  | Medium | Subha/Madhan/Akhila/Bala | 2023-05-12 | 2023-05-15 |  |  | 16
End To End Testing | Testing the whole OrderFulfillment Application |  |  | Medium | Subha/Madhan/Akhila/Bala | 2023-05-16 | 2023-05-16 |  |  | 8
DEMO | Application Demo |  |  | Medium | Subha/Madhan/Akhila/Bala | 2023-05-17 | 2023-05-17 |  |  | 8
Milestone | To Complete the Order-Fulfillment Use Case

## Appian Sprint 6
Q3-Appian Sprint 6 WBS(03-07-2023 to 15-07-2023)
Use Case-Mortgage Loan Processing
Module | CRUD | Interfaces & Process Models Required | Complexity | Assigned To | Planned- Start Date | Planned-End Date | Actual Start Date | Actual End Date | Effort In Hours(Planned) | Actual Hours
Loan Application
| Create Loan Application Form |  |  |  | 2023-07-03 | 2023-07-03 |  |  | 8
| Update Customer Datas- Loan Application Form |  |  |  | 2023-07-04 | 2023-07-04 |  |  | 4
| Getall- Get All Loan Form | Yes | Medium | Bala | 2023-07-04 | 2023-07-04 |  |  | 4
4
8
Pre-Qualification
8
| Validation Api -To check Loan Eligiblity | Yes | Medium | Akhila | 2023-07-03 | 2023-07-03
Loan Pre-Approval
After Validation-Send Email to Customer-Eligible/Not Eligible
Property Appraisal
| Create Form To Enter Property Details | Yes | Medium | Bala | 2023-07-05 | 2023-07-05 |  |  | 8
Validation Api-To Check the loan amount Eligibility(Market Value)
Loan Processing & Underwriting | [8 empty] | 8
| Create Form-To Attach Additional documents(User verification,Check Risk Assesment and Finance doc verification) | Yes | Medium | Akhila | 2023-07-04 | 2023-07-04
| Send Email to Customer-Verification of Documents |  |  |  | 2023-07-05 | 2023-07-05 |  |  | 8
Loan Approval
| Create form-Commitment Form(Approve/Reject Terms) | Yes | Medium | Bala | 2023-07-06 | 2023-07-06 |  |  | 8
| Send Email to customer-(Commitment Letter) |  |  |  | 2023-07-07 | 2023-07-07 |  |  | 8
Closing
| Create Payment Form-(To Pay Loan Insurance Fees) | Yes | Medium | Akhila | 2023-07-06 | 2023-07-06 |  |  | 8
Disbursement
POST-To submit Customer Details
| GET-To get Customer Bank Details | Yes | Medium | Bala | 2023-07-10 | 2023-07-10 |  |  | 8
| Crete form and Api to disburse the loan Amount |  |  |  | 2023-07-11 | 2023-07-11 |  |  | 4
[5 empty] | 2023-07-11 | 2023-07-11 |  |  | 4
Repayment
| POST-Create Api to Get Notification on Loan repay Date | Yes | Medium | Akhila | 2023-07-07 | 2023-07-07 |  |  | 8
| Create Form-To repay Loan Amount |  |  |  | 2023-07-10 | 2023-07-11 |  |  | 16
| Appian-API,Process Model,Interfaces Integration |  |  | Akhila/Bala | 2023-07-12 | 2023-07-13 |  |  | 16
| DEMO ON USECASE |  |  | Akhila/Bala | 2023-07-14 | 2023-07-14 |  |  | 8

## Sprint 7
Q3-Appian Sprint 7 WBS(17-07-2023 to 29-07-2023)
Appian Associate Developer Certification-(Self Learning-Exam Preparation)
Module | Topics | Assigned To | Planned- Start Date | Planned-End Date | Actual Start Date | Actual End Date | Effort In Hours(Planned)
Appian Designer Documentation
| Getting Started |  | 2023-07-17 | 2023-07-17 |  |  | 8
| Designer Space |  | 2023-07-17 | 2023-07-17 |  |  | 4
| Design Objects | Bala/Akhila | 2023-07-18 | 2023-07-18 |  |  | 4
| Designer Tools |  | 2023-07-18 | 2023-07-18 |  |  | 4
8
Appian Data Documentation
| Working with Data in Appian |  | 2023-07-19 | 2023-07-19 |  |  | 8
| Data Objects | Bala/Akhila | 2023-07-19 | 2023-07-19
| Record Types |  | 2023-07-19 | 2023-07-19
| Custom Data Types |  | 2023-07-20 | 2023-07-20
| Data Store Object |  | 2023-07-20 | 2023-07-20
| Connected Systems |  | 2023-07-21 | 2023-07-21
| Integrations |  | 2023-07-21 | 2023-07-21
| Web API's |  | 2023-07-24 | 2023-07-24
Appian Interfaces Documentation
| Learn Interfaces |  | 2023-07-24 | 2023-07-24
| Build Interfaces | Bala/Akhila | 2023-07-25 | 2023-07-25
| Best Practices |  | 2023-07-25 | 2023-07-25
| Reference |  | 2023-07-25 | 2023-07-25
| Create Bank Mortgage-Loan Application in partners portal of appian |  | 2023-07-25 | 2023-07-25
Process Mining Documentation
| Bank Mortgage Loan Data base | Bala/Akhila | 2023-07-26 | 2023-07-26 |  |  | 8
| Get Started |  | 2023-07-26 | 2023-07-26 |  |  | 8
| Mining Prepartion |  | 2023-07-26 | 2023-07-26 |  |  | 4
| Process Mining |  | 2023-02-26 | 2023-07-27 |  |  | 4
| Use case Bank Mortgage Loan completed |  | 2023-07-26 | 2023-07-27 |  |  | 4
| Administrators |  | 2023-07-27 | 2023-07-27 |  |  | 8
| Demo Completed of Bank Mortagage Loan Application | Bala/Akhila | 2023-07-27 | 2023-07-27 |  |  | 8
| Assesment On Appian Documentation Courses |  | 2023-07-28 | 2023-07-28