## Appian Track Sheet
Appian CoE Daily Tracker - Online Exam Application
S.No | Task | SubTask | Assigned To | Assigned By | Planned Date |  | Actual Start Date |  | planned Hours | Actual Hours | Status | Comments
[5 empty] | Start Date | End Date | Start Date | End Date
1 | Admin Site for Uploading Excel Data's | Data Store for Uploading Questions |  |  | 27/12/23 | 27/12/23 | 28/12/23 | 28/12/23 | 4 | 2 | Completed
|  | Constant for all data objects & Interfaces to upload excel data's |  |  | 27/12/23 | 27/12/23 | 28/12/23 | 28/12/23 | 4 | 6 | Completed
|  | Process Model- Excel Data smart services | Akhila | Madhan | 28/12/23 | 30/12/23 | 29/12/23 | 30/12/23 | 16 |  | In Progress | While uploading data, it's getting stored in document but in database records not getting updated/stored
|  | Site for Admin Portal |  |  | 30/12/23 | 30/12/23 | 30/12/23 | 30/12/23 | 4 |  | Yet to start
|  | Testing the scenarios |  |  | 30/12/23 | 30/12/23 | 30/12/23 | 30/12/23 | 4
|  | Total Hours | [6 empty] | 32 Hours
2 | User Site for Attending Exam
|  | Interfaces for retrieving data's from database- Record Type(Grid)/CDT |  |  | 27/12/23 | 28/12/23 | 28/12/23 | 29/12/23 | 16 |  | In Progress | Able to retrieve data's to interface but option colum we need to enable checkbox in record grid. Working on that.
|  | Validation- Actual answer with expected Anwer | Bala | Madhan | 29/12/23 | 30/12/23 | 30/12/23 | 2024-02-01 | 10 |  | Yet to start
|  | Site for User Portal |  |  | 30/12/23 | 30/12/23 | 2024-02-01 | 2024-02-01 | 2 |  | Yet to start
|  | Testing the scenarios |  |  | 30/12/23 | 30/12/23 | 2024-02-01 | 2024-02-01 | 4
|  | Total Hours | [6 empty] | 32 Hours
|  | Demo on Usecase |  |  | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01